## Group13_Estimated_Effort
Task Name: (Dependencies top to bottom) | Scheduling project | Team 13 | [6 empty] | Nawaf | Anisha | Daniel | stanley | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 5 |  | 2
|  | Class schedule architecutre | Project Manager | Nawaf , Anisha | 5 |  | 2 |  | 2 | 0 | 0 | 0 | 0
| Requirements |  |  |  |  | 8 |  | 11.5 |  |  |  |  | 0
|  | Get the umkc classess schedule | Project Manager | Anisha,Stanley,Nawaf,Daniel | 2 |  | 3 |  | 1 | 1 | 1 | 0 | 3
|  | Discuss the project in the daily meeting | Project Manager | Anisha,Stanley,Nawaf,Daniel | 3 |  | 4 |  | 2 | 1 | 1 | 0 | 4
|  | analysis the project | Project Manager | Anisha,Stanley,Nawaf,Daniel | 3 |  | 4.5 |  | 1 | 2 | 0.5 | 1 | 4.5
| Documentation |  |  |  |  | 22 |  | 25.5
|  | Project Charter |  | Nawaf | 2.5 |  | 3.5 |  | 0 | 3 | 0 | 0.5 | 3.5
|  | Release Plan |  | Daniel | 2 |  | 1 |  | 0.5 | 0 | 0.5 | 0 | 1
|  | Requirements Document |  | Anisha | 3 |  | 5 |  | 0.5 | 0.5 | 0 | 1 | 2
|  | Project Plan |  | Stanley | 3.5 |  | 5.5 |  | 0 | 0 | 0 | 1 | 1
|  | Architecture Document |  | Daniel | 4 |  | 3.5 |  | 0.5 | 2 | 1 | 0 | 3.5
|  | Test Report |  | Nawaf | 5 |  | 3 |  | 1 | 2 | 0 | 0 | 3
|  | User Guide & System Admin Doc |  | Anisha,Stanley,Nawaf,Daniel | 2 |  | 4 |  | 0.5 | 2 | 0.5 | 1 | 4
Coding | [12 empty] | 0
Iteration 1: | Development |  |  |  |  | 36 |  | 32 |  |  |  |  | 0
|  | Determine the classes that are needed | Developer | Nawaf , Anisha | 1 |  | 3 |  | 0 | 0 | 1 | 2 | 3
|  | Research and learn new language and environment | Developer | Daniel,Stanley | 11 |  | 19 |  | 1 | 0 | 10 | 8 | 19
|  | Set up the schedule for classess | Developer | Nawaf , Anisha | 8 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Brainstorm for code | Developer | Stanley | 5 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Implement classes | Developer | Nawaf,Anisha,Daniel,Stanley | 7 |  | 10 |  | 0 | 0 | 5 | 5 | 10
|  | Write code to store user name and professor name | Developer | Stanley | 2 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Unit Testing | Developer | Stanley | 2 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Analysis |  |  |  |  | 6.5 |  | 6
|  | System Testing | Tester | Nawaf,Anisha | 2.5 |  | 2 |  | 1 | 1 | 0 | 0 | 2
|  | Bug fix as required | Tester, Developer | Daniel,Stanley | 2 |  | 2 |  | 0 | 0 | 1 | 1 | 2
|  | Evaluate needs for next iteration | Project Manager | Nawaf,Anisha | 2 |  | 2 |  | 1 | 1 | 0 |  | 2
Coding | [6 empty] | 0 | [5 empty] | 0
Iteration 1: | Development |  |  |  |  | 34 |  | 0
|  | Design interface layout | Developer | Nawaf , Anisha, Daniel, Stanley | 6 |  |  |  | 0 | 0 | 0 | 0 | 0
|  | Design professor model | Developer | Nawaf, Anisha | 2 |  |  |  | 0 | 0 | 0 | 0 | 0
|  | Start on UI framework | Developer | Daniel | 6 |  |  |  | 0 | 0 | 0 | 0 | 0
|  | Create navbar at top of the website displaying clickable tabs | Developer | Stanley | 4 |  |  |  | 0 | 0 | 0 | 0 | 0
|  | Configure database | Developer | Stanley, Daniel, Nawaf, Anisha | 4 |  |  |  | 0 | 0 | 0 | 0 | 0
|  | Create professor model in Django/Python | Developer | Stanley, Daniel | 4 |  |  |  | 0 | 0 | 0 | 0 | 0
|  | Create professor table on database tab | Developer | Stanley | 4 |  |  |  | 0 | 0 | 0 | 0 | 0
|  | Allow user to create professor model | Developer | Daniel | 2 |  |  |  | 0 | 0 | 0 | 0 | 0
|  | Allow user to edit professor models | Developer | Stanley, Daniel | 2 |  |  |  | 0 | 0 | 0 | 0 | 0
| Analysis |  |  |  |  | 7
|  | Test if links to tabs are working properly | Tester | Nawaf, Anisha | 2.5 |  |  |  | 0 | 0 | 0 | 0 | 0
|  | Professor model tests | Tester | Nawaf, Anisha | 2.5 |  |  |  | 0 | 0 | 0 | 0 | 0
|  | Evaluate needs for next iteration | Project Manager | Anisha, Nawaf | 2 |  |  |  | 0 | 0 | 0 | 0 | 0